## 工作表1
Task Name | Start Date | Due Date | Status | Progress (%) | Assigned To | Priority
Initialize github repository and structured the folder hierarchy for data (raw, curated, marts), documentation, and source code. | 2025-10-24 | 2025-10-26 | Completed | 100 | Chen | High
Database schema design | 2025-10-24 | 2025-10-26 | Completed | 100 | Chen | High
Established data partition rules for Parquet snapshots | 2025-10-24 | 2025-10-26 | Completed | 100 | Chen | High
Begin implementing the ETL pipeline for securities and price ingestion | 2025-10-26 | 2025-10-31 | In Progress | 0 | Chen | High
Define the factor computation layer (momentum, value, quality) and backtest logic. | 2025-10-26 | 2025-11-05 | In Progress | 0 | Chen | Medium